## Project
Project Information
So Called Engineers (SCE)
Team members | TE Carter
SJ Du Plessis
CF Greyling
System Breakdown
On the left the Upper level system operational archetecture is drawn
Is the Inteface for each element
TE Carter work
SJ du Plessis work
CF Greyling work
[6 empty] | This is then shown with only the interfaces |  | Block diagram of the whole circuit | From this the system is then broken up into units
Work Breakdown and Allocation
Member | Function responsible for | Additional Tasks
TE Carter | DCDC Convertor 1 I/F 2.0 Unit 3 | Functional analysis diagram
| DCDC Convertor 2 I/F 2.2 Unit 3 | Research for I/F responsible for
| DCDC Convertor 3 I/F 2.4 Unit 3 | List and price components needed for I/F responsible for
| Phone Charger I/F 5.2 Unit 5 | Begin working on ELO 5 and portfolio
| LED Light Driver I/F 3.7 Unit 3 | Compile the budget
Buy components
SJ Du Plessis | Arduino control and programming Unit 2 | Define all interfaces
| Battery charging with PWM I/F 1.7.1, 3.6, 3.5 Unit 2 | Research for I/F responsible for
| LED light control with PWM Unit 3.7 | List and price components needed for I/F responsible for
| Additional Trigger I/F 3.4 and 3.1 Unit 2 | Work further on Functional Analysis
| HMI control with LEDs I/F 3.9 Unit 2 | Begin working on ELO 5 and portfolio
Submit and compile all documents
CF Greyling | Solar Charge Unit and PSU I/F 1.0 Unit 1 | Functional architecture
| Battery I/F 4.1 Unit 1 | Research for I/F responsible for
| 220 V Mains Input (Optional) (no longer included) | Compile the power budget
| Solar Panel I/F 1 Unit 1 | Begin working on ELO 5 and portfolio
List and price components needed for I/F responsible for
Project Schedule
Timeline
Date | Description | Timeline | notes
2017-07-17 | Project initiation | 1
2017-08-10 | Functional Analysis Test | 2
2017-08-10 | Functional Analysis Complete 2 levels | 1
2017-08-14 | Preliminary Design Complete | 3
2017-08-28 | Work done as discussed in class in preperation for 30% demonstration | 2
2017-08-31 | 30% Completion Milestone | 4
2017-09-04 | Finalise who is working on which part of the circuit | 4
2017-09-07 | Order Compenents and finalise wiring diagram | 4
2017-09-28 | Start Assembling Circuit | 4
2017-09-30 | 50% Completion Milestone | 4
2017-10-27 | 80% Completion Milestone | 3
2017-11-10 | 100% Completion Milestone | 4
2017-11-16 | Demonstration | 3
Progress Tracking
Project Status
| % Complete | Green | Amber | Red | Description
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6 | 20% |  |  |  | Some confusion as to what has to be done for the 30% milestone
Week 7 | 30% demo
Week 8
Week 9
Week 10 | 50% demo |  |  |  | According to 50 % assesement we are at 88% of the 50 % therefore still green
Week 11 | Start building |  |  |  | There is still unclarity on the USB port and another group member has been put in charge of the USB port as well as the optocoupler
Week 12 |  |  |  |  | Only the LED has been built and tested there seems either to be a problem with the ciruit or the Arduino code.
Week 13 | 60% |  |  |  | The USB chips have not arrived yet and the correct diodes must be bought for the charger and the correct capacitors for the DCDC convertors
Week 14 |  |  |  |  | The charger and DCDC have been built but don't seem to work.
Week 15 |  |  |  |  | The lecturer has been consulted and it has been discovered that the DCDC chips and USB chips are falulty, these devicesa are now on track the charger also works it just does not want to switch.
Week 16 | 80% demo |  |  |  | All the documentation has been corrected and most part have been integrated the charger just does not want to switch and the lecturer will be consulted on this matter.
Week 17 | 100% demo |  |  |  | Finalising documentation and the charging circuit now works, just making the circuit more presentable,
Week 18 | Project finished |  |  |  | Project finalised and ready for the final demonstration
TE Carter

## TE Carter
Member Information
Member name | TE Carter
Expertise | Documentation and Hardware
Unit Breakdown
Member Work Breakdown
Function responsible for | Additional Tasks
DCDC Convertor 1 I/F 2.0 Unit 3 | Functional analysis diagram
DCDC Convertor 2 I/F 2.2 Unit 3 | Research for I/F responsible for
DCDC Convertor 3 I/F 2.4 Unit 3 | List and price components needed for I/F responsible for
Phone Charger I/F 5.2 Unit 5 | Begin working on ELO 5 and portfolio
LED Light Driver I/F 3.7 Unit 3 | Compile the budget
Buy components
Timeline
Date | Description | Timeline | notes
2017-07-17 | Project initiation | 1
2017-08-08 | Design Functional Analysis | 1
2017-08-10 | Functional Analysis Test | 2
2017-08-14 | Preliminary Design Complete | 4
2017-08-28 | Work done as discussed in class in preperation for 30% demonstration | 4
2017-08-31 | 20% Completion Milestone | 3
2017-09-04 | Research and design wiring diagram for components | 2
2017-09-06 | Finalise wiring daigram and make list of components | 1
2017-09-07 | Order components | 3.5
2017-09-08 | 30% Completion Milestone | 4.5
2017-09-28 | Begin Assembling Components | 5
2017-09-30 | 50% Completion Milestone | 4
2017-10-27 | Ensure all subcircuits work and test and document | 5
2017-10-30 | Start intergrating and testing the integrated circuitx | 5.5
2017-10-30 | 80% Completion Milestone and documentation update | 3
2017-11-10 | 100% Completion Milestone | 4
2017-11-16 | Demonstration | 3
Progress Tracking
Individual progress Status
| % of work allocated to member completed | Green | Amber | Red | Description
Week 1 | 100%
Week 2 | 100%
Week 3 | 100%
Week 4 | 100%
Week 5 | 100%
Week 6 | 100%
Week 7 | 100%
Week 8 | 100%
Week 9 | 100%
Week 10 | 50% demonstration |  |  |  | Fallen behind on documentation for 50% demo
Week 11 | Need to start building |  |  |  | Components have arrived behind on building
Week 12 |  |  |  |  | The LED has been built and tested with the signal generator and another persons code.
Week 13 |  |  |  |  | The LED has been soldered onto the veroboard and does not work with the arduino code
Week 14 |  |  |  |  | No other components have been built still waiting for USB chips and finding the correct capacitors for the DCDC.
Week 15 |  |  |  |  | The DCDC has been built but does not work, consulted with lecturer and found the chips were blown, the same is now true for the USB chips could be due to soldering them on. New DCDC chips have been used by classmates and USB ports have been bought because to reorder will take to long
Week 16 | 80% demo |  |  |  | All sub circuits work for this member the interface document has been updated but the lecturer will be asked if it is correct and the functional flow diagram will also be redone and the lecturer will be asked if the new one is correct.
Week 17 | 100% demo |  |  |  | Need to update all documentation and conduct tests on the whole system and record and document the information
Week 18 | Project ends |  |  |  | Ensure all documents are up to date

## SJ Du Plessis
Member Information
Member name | SJ Du Plessis
Expertise | Software expertise including programming
Unit Breakdown
Member Work Breakdown
Function responsible for |  | Additional Tasks
Arduino control and programming Unit 2 |  | Spesification of Interfaces
Battery charging with PWM I/F 1.7.1, 3.6, 3.5 Unit 2 |  | RF Flow combined block diagram
LED light control with PWM Unit 3.7 |  | PV panel characterisation
Additional Trigger I/F 3.4 and 3.1 Unit 2 |  | Work further on Functional Analysis
HMI control with LEDs I/F 3.9 Unit 2 |  | Battery charging (PWM)
Begin working on ELO 5 and portfolio
Submit and compile all documents
Member Schedule
Timeline
Date | Description | Timeline | notes
2017-07-17 | Project initiation | 1
2017-08-10 | Functional Analysis Test | 2
2017-08-12 | Spesification of Interfaces | 2
2017-08-14 | Preliminary Design Complete | 1
2017-08-28 | Work done as discussed in class in preperation for 30% demonstration | 2
2017-08-31 | 30% Completion Milestone | 3
2017-09-04 | PV panel characterised | 3
2017-09-30 | 50% Completion Milestone | 4
2017-10-27 | 80% Completion Milestone | 3
2017-11-10 | 100% Completion Milestone | 4
2017-11-16 | Demonstration | 3
Progress Tracking
Individual progress Status
| % of work allocated to member completed | Green | Amber | Red | Description
Week 1 | 100%
Week 2 | 100%
Week 3 | 100%
Week 4 | 100%
Week 5 | 100%
Week 6 | 100%
Week 7 | 100%
Week 8 | 100%
Week 9 | 100%
Week 10 | 50% demonstration |  |  |  | Fallen behind on documentation for 50% demo
Week 11 | Need to start building |  |  |  | Components have arrived behind on building
Week 12 | 60% |  |  |  | Test week
Week 13 |  |  |  |  | Helped with LED layout and solderd to veroboard. Small amount of diming with Arduino. Arduino switching correctly on oscilliscope.
Week 14 |  |  |  |  | Still not sure what was wrong with the LED circuit. Characterized the Solar panel in the sun and compared results against datasheet
Week 15 |  |  |  |  | Coded on main program, still wanting on other cicruits to test them for functionality and to finalize the code. Focused on other subjects practicals and tests.
Week 16 | 80% demo |  |  |  | LED circuit fault found. LED current limited with to high resistance. Replaced 1k ohm resistor with two 1.2 ohm 5W resistors. Code dimes the LED. Helped with the DCDC convertors as well as the charge circuit. The charge circuits had an fault and the layout on the veroboard made it hard to connect loads. Redesign the layout and made the load connects easier.
Week 17 | 100% demo |  |  |  | Document the new designs and finalize the programming of the Charger and LED.
Week 18 | Project ends |  |  |  | Finalize final errors and final test on designs

## CF Greyling
Member Information
Member name | CF Greyling
Expertise | Hardware, Documentation and Software such as Excel, RF Flow
Unit Breakdown
Member Work Breakdown
Function responsible for |  | Additional Tasks
Solar Charge Unit and PSU I/F 1.0 Unit 1 |  | Functional archetecture
Battery I/F 4.1 Unit 1 |  | Research for I/F responsible for
220 V Mains Input (Optional) (no longer included) |  | List and price components needed for I/F responsible for
Solar Panel I/F 1 Unit 1 |  | Compile the power budget
Work on ELO 5 and portfolio
Document team work
Document meetings
Document requirements
Simulations and Circuit diagrams of I/F responsible for
Timeline
Date | Description | Timeline | notes
2017-07-17 | Project initiation | 1
2017-08-10 | Functional Analysis Test | 2
2017-08-14 | Preliminary Design Complete | 1
2017-08-28 | Work done as discussed in class in preperation for 30% demonstration | 2
2017-08-31 | 30% Completion Milestone | 3
2017-09-30 | 50% Completion Milestone | 4
2017-10-27 | 80% Completion Milestone | 3
2017-11-10 | 100% Completion Milestone | 4
2017-11-16 | Demonstration | 3
Progress Tracking
Individual progress Status
| % of work allocated to member completed | Green | Amber | Red | Description
Week 1 | 100%
Week 2 | 100%
Week 3 | 100%
Week 4 | 100%
Week 5 | 100%
Week 6 | 100%
Week 7 | 100%
Week 8 | 100%
Week 9 | 100%
Week 10 | 50 % milestone |  |  |  | 93% on evaluation from lecturer
Week 11 | start building |  |  |  | components have arrived but behind on building schedule
Week 12 |  |  |  |  | redesign circuit without mains 220V power supply
Week 13 | 60% |  |  |  | Correct Scottky diodes must be bought for the power supply management
Week 14 |  |  |  |  | Learn how to solder. Built the charge controller circuit and the diode circuit. Ready for testing next week.
Week 15 |  |  |  |  | Discovered mistake in diode circuit, unsolder main componants from board, resolder correct circuit, use node checking. Diode circuit fixed and working, solar panel tested and working, battery tested and working. Test Arduino with charging switch.
Week 16 | 80% demo |  |  |  | Documentation on track. Diode is switching the circuit. Battery working. Solar Panel working. Charge controller functional but will not switch correctly. Ask Prof if the ground is where the mistake is. Therefore not all individual componants working and not on track for 80% milestone. Would rate work at 80% of the 80% milestone.
Week 17 | 100% demo |  |  |  | Test integerated system. Document the testing. Complete documentation.
Week 18 | Project ends |  |  |  | Ensure all documentation is complete

## Minutes of Meetings
Minutes of Meetings
Meeting 1
Date | 2017-08-08
Time | 0.58333
Chairman | TE Carter
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | Progress on schedule
Issues / Risks and Mitigations | No risk identified |  |  | (Perform progress tracking on the tracking schedule as in each members' and the project's worksheet.)
Decisions | Functional Flow Diagram |  |  | (Use the Risks and Mitigations worksheet to identify, track and mitigate risks.)
| Functional Architecture Design |  |  | (Document all decisions made by the team.)
| Specification of interfaces |  |  | (List all actions to be taken to ensure progress and mitigate risks.)
Actions | Allocated work | TE Carter | Functional Flow Diagram
|  | SJ Du Plessis | Specification of interfaces
|  | CF Greyling | Functional Architecture Design
Meeting 2
Date | 2017-08-21
Time | 0.54167
Chairman | SJ Du Plessis
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | Progress on schedule
Issues / Risks and Mitigations | No risk identified
Decisions | Members work allocation
Actions | Allocated work | TE Carter | DC to DC converter
LED
|  | SJ Du Plessis | ARDUINO
Programming
|  | CF Greyling | Solar charge unit
Battery
USB charger
Meeting 3
Date | 2017-08-24
Time | 0.60417
Chairman | CF Greyling
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | 20% complete
Issues / Risks and Mitigations | Uncertainty of work due for 30% deadline
Decisions | Portfolio | ELO 5
ELO 8
Actions | Allocate individual and group work between members
Agree to ask for clarification (in Monday 28th class) of work due up for 30% milestone
Meeting 4
Date | 2017-08-28
Time | 0.47917
Chairman | SJ Du Plessis
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Take note this meeting was held with Prof Holm in order to clear up some uncertainties about the circuit
Agenda
Progress Tracking | By 07-Sept-17 30% Complete
Issues / Risks and Mitigations | The solar panel connectors
The price of the solar panel connectors
Decisions | How the circuit will look this can be seen in the Figure in this meeting
Actions | Simulate and finalise the wiring diagram by 05-Sept-17
Create a list and order components by 07-Sept-17
The solar panel connectors is a MC4 connector
Meeting 5
Date | 2017-09-04
Time | 0.33333
Chairman | CF Greyling
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | 27%
Issues / Risks and Mitigations | The connectors on the solar panel
Other connector are expensive
Switch between power input components
220 V AC input from mains connection to circuit
Solar charge unit circuit
Unsure about pricing of componants MPS
Arduino connection to charger
Arduino connection to LED light driver
Decisions | determine the price o fcomponants
Actions | Make contact with MPS about componant pricing
Meeting 6
Date | 2017-09-11
Time | 0.33333
Chairman | TE Carter
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | 30%
Issues / Risks and Mitigations | progress of project
Decisions | EMC of project
PCB Layout
Design for DC to DC converters
Actions | design for the DC to DC converter finalised
will use other way to lay out circuit than PCB
Meeting 7
Date | 2017-09-18
Time | 0.33333
Chairman | SJ Du Plessis
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | 40%
Issues / Risks and Mitigations | Risks | 50% deadline | Paperwork
Show of progress
| Mitigation | informed on what is due fir 50%
Decisions |  | 50% deadline requirements
State base diagram
Charactirization
Actions | stock taken of progress
begin work for deadline
Meeting 8
Date | 2017-09-23
Time | 0.33333
Chairman | CF Greyling
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | 45%
Issues / Risks and Mitigations | 50% deadline may not be complete
Decisions | Work allocation for 50% deadline
decided that we will complete work up untill where we are giving an honest representation of work progress
Will work in vacation starting Tuesday 12 pm
Actions | Design module is set as priority
Meeting 9
Date | 2017-10-09
Time | 0.33333
Chairman | CF Greyling
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | 50%
Issues / Risks and Mitigations | DC to DC converter not finding the correct ceramic caps
Decisions | Continue building
Continue documenting
try to finish work before the exam
Actions | general 50% assesment
Meeting 10
Date | 2017-10-16
Time | 0.33333
Chairman | TE Carter
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | 60%
Issues / Risks and Mitigations | 50-60% assesment and feedback Monday 13:00 clash with LLAW class
Decisions | Testability
safety
try to finish work before the exam
Actions | mitigation of risk of assesment
Meeting 11
Date | 2017-10-19
Time | 0.66667
Chairman | SJ Du Plessis
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | 60%
Issues / Risks and Mitigations | Time for combined building limited
Decisions | safety
HIRA
formal lessons at an end
Monday resubmission for documentations
Actions | Discuss safety in the project
single point of failure
Meeting 12
Date | 2017-10-26
Time | 0.41667
Chairman | CF Greyling
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | 65%
Issues / Risks and Mitigations | DC to DC converter chips blown, new circuit designed
charge controller circuit not working must rebuild
USB chips not functioning
Decisions | new DC to DC conerter circuit designed
must resolder charge controller circuit
date set for 27th to continue building
new design of USB charger decided on
Actions | work on 27th
porfolio on design updates
Meeting 13
Date | 2017-10-27
Time | 0.33333
Chairman | TE Carter
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | 70%
Issues / Risks and Mitigations | 80% milestone on the way
Charger does not want to switch
Decisions | Work at home in the weekend
do more testing on the charge controller
assemble most of the componants in the control panel
Actions | do risk mitigation of the charge controller
update design portfolio and project management file
Meeting 14
Date | 2017-11-09
Time | 0.52083
Chairman | SJ Du Plessis
Attendance list | TE Carter
SJ Du Plessis
CF Greyling
Agenda
Progress Tracking | 90%
Issues / Risks and Mitigations | 100% demo on the way and final demo
The coding is not yet complete and a lot of documentation still needs to be done.
Decisions | Work on the portfolio 11-Nov-2017
Submit portfolio to demi on 13-Nov-2017
Improve portfolio 14-Nov to 16-Nov-2017
Do final tests on 11-Nov-2017
Actions | Do final documentation and testing 11-Nov-2017
Send portfolio to demi 13-Nov-2017
Correct and prepare portfolio for submission.

## Risks and Mitigations
Issues / Risks and Mitigations |  |  | * A risk is something that hasn't happened yet but has some probability of occurring. An issue is essentially a risk that has happened.
|  | Description of issue / risk | The description can be classified as a | The type of risk / issue | (1-5) | What will happen when this risk event actually happens? | What needs to be done to reduce this risk. | Who will work on this risk. | RAG for mitigation eg green if mitigated
Risk No | Date | Description of Issue / Risk | Issue / Risk* | Type | Severity | Impact | Mitigation / Action | Responsible person | Mitigated | notes on mitagation
1 | 2017-08-24 | Confusion as to what is due for the 30% milestone | Issue | Project | 3 | Penalisation for incomplete work | Complete work up to where is possible and ask in Monday (28th) class for clarification | All members
2 | 2017-08-31 | Components not ordered | Risk | Project | 3 | Behind schedule may not finish project | Order components ASAP | All members
3 | 2017-08-31 | MOSFET or PSU unsure | Issue | Technical | 3 | PSU does not work | Find someone to help | CF Greyling
4 | 2017-08-31 | The timeline to build project | Risk | Technical | 2 | Do not complete project and get penalised for it | Better time management | All members |  | time continues to be an obstical
5 | 2017-08-31 | Design not finished | Risk | Technical | 5 | Do not finish in time | Finish the design within the week, change focus to design | All members
6 | 2017-08-31 | Time components take to order | Risk | Technical | 2 | Do not have enough time to finish the project | Order components with leniency | All members |  | First componants ordered received
7 | 2017-08-31 | Don't know what will happen if deadline is not met | Risk | Project | 4 | Penalty | Unable to finish project | All members |  | will not be late
8 | 2017-08-31 | Help with the thermal design of the LED | Issue | Project | 3 | LED does not work | Determine how the LED works | TE Carter
9 | 2017-08-31 | Simulation and wiring not done for components | Issue | Project | 5 | Deadline not met | Must do within the week | All members
10 | 2017-08-31 | Datasheets and application notes must be downloaded and added to the portfolio | Issue | Technical | 5 | Deadline not met | Must to within the week | All members
11 | 2017-08-31 | Not sure how to design a DCDC convertor | Issue | Technical | 3 | Technical issue | MPS design simulation for DCDC and populate porfolio | TE Carter
12 | 2017-08-31 | Not sure how to design an LED driver | Issue | Technical | 3 | Technical issue | Do research | TE Carter
13 | 2017-08-31 | Not 100% sure how the circuit looks | Risk | Technical | 5 | Build the circuit incorrectly | Do research | All members
14 | 2017-08-31 | Have nothing to measure against at present | Risk | Technical | 5 | Become behind schedule | Get the solar panel to do testing on | SJ Du Plessis |  | Test completed
15 | 2017-08-31 | PC board layout and the thermal design of the LED | Risk | Technical | 3 | Cannot order components before design | Do research | TE Carter |  | No PC board layout
16 | 2017-09-04 | The connectors on the solar panel | Issue | Technical | 3 | Don’t know how to use connectors | Do research | SJ Du Plessis |  | Connectors found but are very expensive
17 | 2017-09-04 | Other connector are expensive | Risk | Project | 3 | The price of new connectors are expensive | Consult with lecturer | SJ Du Plessis |  | less expensive connectors found but still costly
18 | 2017-09-04 | Switch between power input components | Issue | Technical | 3 | Technical issue | Consult with lecturer | All members |  | Switch with diodes between supplies
19 | 2017-09-04 | 220 V AC input from mains connection to circuit | Issue | Technical | 2 | Technical issue | Consult with lecturer | CF Greyling |  | Will add if there is extra time and resources left (Optional Extra)
20 | 2017-09-04 | Solar charge unit circuit | Issue | Technical | 3 | Technical issue | Consult with lecturer | CF Greyling
21 | 2017-09-04 | Unsure about pricing of componants MPS | Risk | Technical | 2 | Over budget | Make contact with Mr de Klerk from MPS | All members |  | Consulted with MPS employee and determined the cost of componants
22 | 2017-09-04 | Arduino connection to charger | Risk | Technical | 3 | Technical issue | Consult with lecturer | CF Greyling, SJ Du Plessis
23 | 2017-09-04 | Arduino connection to LED light driver | Risk | Technical | 3 | Technical issue | Consult with lecturer | TE Carter, SJ Du Plessis
24 | 2017-09-05 | Courier cost and time for componants from MPS | Risk | Project | 3 | extra cost may cause project to exceed the budget and the extra time couruer takes may delay the project dangerously | Consult Mr de Klerk at MPS and the finance at NWU | All members
25 | 2017-09-05 | Payment method for componants at MPS | Issue | Technical | 2 | Financial issue | Consult finance for project | All members
26 | 2017-09-06 | USB chip | Issue | Technical | 2 | Technical issue | Do more research on different kinds of usb chips | CF Greyling |  | Differtent usb charger
27 | 2017-09-23 | some componants still need to be ordered | Risk | Technical | 2 | Componants not delivered with in time of completetion | order all componants ASAP | All members |  | Componants ordered
28 | 2017-09-23 | Due date for 50% completion moved ahead from 30 to 26 September | Risk | Project | 4 | 50% Completion not on time | Ask for extention of time and complete work | All members |  | extention received till the end of 27th
29 | 2017-09-23 | Schottky diode sufficient for power switch? | Risk | Technical | 3 | Circuit will not work if diode is insufficient | Do more research on properties of different diodes | CF Greyling |  | Correct diode used
30 | 2017-10-04 | 50% milestone may not be up to standard | Risk | Project | 2 | Behind schedule may not finish project | Be a accurate as possible with porject | All members |  | 50% milestone assesment was successful
31 | 2017-10-06 | cannot find the correct ceramic caps | Issue | Technical | 3 | DC to DC converter will not be able to work with polarised | Find a store that has the corrct ceramic cap | TE Carter |  | Found Cermaic caps of the correct value
32 | 2017-10-16 | schedule clash between LLAW 221 | Risk | Project | 2 | Might not be able to be at the assesment | Talk to Prof Holm about a time slot | All members |  | Not needed to go As the group got above 80%
33 | 2017-10-26 | DC to DC converters are not working because the chips aren't working | Issue | Technical | 3 | Technical issue | The DCDC chips aren't working | TE Carter |  | Find new chips and rebuild, which was done the moment it was discovered that the chips don't work.
34 | 2017-10-26 | USB charger does not work because the chips aren't working | Issue | Technical | 2 | Technical issue | The USB chips don't work either | TE Carter |  | Buy a USB port circuit
35 | 2017-10-26 | the battery charge controller works but it does not switch | Issue | Technical | 3 | Technical issue | The charger works but it is not switching | CF Greyling |  | charger working

## Trade off study
1. Display |  |  |  |  | Aspects affecting:
|  | LCD | LED | 7 segment | Reliability | Ease of use
0.5 | Cost | 3 | 10 | 7 | manufacturers | who is the user
0.3 | Reliability | 6 | 9 | 7 | amount of componants in part | capablity of user
0.2 | Ease of use | 5 | 8 | 6 | breakability | maintenance
|  | 4.3 | 9.3 | 6.8 | ability to work during impotant circumstances | installment
choice: | LED
2. Solar Panel
|  | 30W | 40W | 50W
0.4 | Cost | 8 | 7 | 4
0.5 | Reliability | 3 | 7 | 8
0.1 | Ease of use | 7 | 7 | 7
|  | 5.4 | 7 | 6.3
choice: | 40 W panel
3. Charge unit
|  | MOSFET P | Buy | LM138
0.17 | Cost | 8 | 4 | 9
0.38 | Reliability | 6 | 9 | 2
0.35 | Education | 8 | 1 | 6
0.1 | Difficulty to build | 3 | 9 | 6
1 |  | 6.74 | 5.35 | 4.99
choice: | MOSFET P-channel
4. Battery
|  | 12 V 7.5Ah | 9V 7.5Ah | 12V 9A
0.35 | Cost | 6 | 7 | 6
0.25 | Availability | 2 | 5 | 8
0.4 | power supply | 7 | 3 | 9
|  | 5.4 | 4.9 | 7.7
5. USB Protection
|  | MCP73831/2 | L200 | MP62130
0.3 | Cost | 9 | 5 | 8
0.5 | Protection | 8 | 5 | 10
0.4 | Heat Dissipation | 8 | 3 | 9
|  | 9.9 | 5.2 | 11
This option is no longer used due to availability.
6. USB Protection
|  | MCP73831/2 | Already made USB Port | MP62130
0.15 | Cost | 9 | 4 | 8
0.4 | Protection | 8 | 10 | 10
0.2 | Availabilty | 8 | 10 | 2
0.25 | Heat Dissipation | 8 | 9 | 9
|  | 8.15 | 8.85 | 7.85
This is why it has been decided to buy a charging port with all protection already in the circuit.
7. Arduino's
|  | Uno 3 | Nano | Micro
0.15 | Cost | 3.2 | 6.4 | 3.5
0.4 | Installation | 8 | 5 | 5
0.25 | Availabilty | 9 | 2 | 5
0.2 | Functionablity | 6 | 7 | 8
|  | 7.13 | 4.86 | 5.375
The Arduino Uno 3 is selected

## Power Budget
Power Supply Components | Rated Ah | Rated V | Power W
Solor Panel | 2.2222 | 18 | 40
Charger | 7 | 12 | 84
Battery 1 | 7 | 12 | 84
Battery 2 | 7 | 12 | 84
Battery Series | 7 | 24 | 168
Battery Parallel | 14 | 12 | 168
Interface 1.1 (Solar Panel - Charger )
Time to fully Charge | 3.15 | hours
6 hour charging | 13.3333 | Ah
8 hour charging | 17.7778 | Ah
Interface 1.2 (Charger - Battery)
Time to charge Battery 1 | 1 | hour
Time to charge Battery 2 | 1 | hour
Time to charge Battery Series | 1 | hour
Time to charge Battery Parallel | 2 | hour
Interface 2.1 (Charger - HMI)
| Rated A | Rated V | Power W
HMI / Alarm | 0.83333 | 12 | 10
Interface 2.2 (Charger - DC DC Convertor)
| Rated A | Rated V | Power W
DC DC Convertor 1 | 1.5 | 12 | 10
Interface 2.3 (Charger - USB Port)
| Rated A | Rated V | Power W
USB Port | 0.5 | 5 | 2.5
Interface 3.1 (DC DC Convertor 1- Arduino)
| Rated A | Rated V | Power W
Arduino | 0.5 | 7 | 3.5
Interface 4.1 (Arduino - DC DC Convertor)
| Rated A | Rated V | Power W
DC DC Convertor 2 | 0.5 | 7 | 3.5
Interface 5.1 (DC DC Convertor 2- USB Port)
| Rated A | Rated V | Power W
USB Port | 1.5 | 5 | 7.5
Total Power in system | 37 | W
Thus a solar panel supplying 40 W will be enough.

## BOM
Bill of material
quantity | Price ® | Componant | Volts | Ampere | Ohm | uF | Watt | Description
1 |  | Battery | 12 | 7.5
5 |  | Diode | [5 empty] | schottky
2 |  | Resistor |  |  | 2k
3 |  | Resistor |  |  | 10k
1 |  | Transorb - Transient Voltage Suppressors | 33 |  |  |  |  | its for lightning prortection
2 |  | Fuses
3 |  | USB port | [5 empty] | A-type felame port
2 |  | Capacitor |  |  |  | 0.1
2 |  | Capacitor |  |  |  | 100
2 |  | Diode Zener | 5 | 1
1 |  | Transistors ( 2N3904 or 2N2222)
2 |  | LED RED
2 |  | LED Green
1 |  | LED Blue
soldering iron
perferated board or what are we going to build on
2 |  | fuse holder
2 |  | fuse
1 |  | heatsink
header pins male
header pins female
header pins rightangle
3 |  | screw terminals 2 pin
1 |  | screw terminals 6 pin
1 |  | Solar Panel

## Financial Budget
Component | Amount | Price
Resistors
100 kΩ | 10 | 1
20 kΩ | 10 | 1
1.8kΩ | 10 | 1
10kΩ | 10 | 1
200Ω | 10 | 1
27kΩ | 10 | 1
1.5kΩ | 10 | 1
33kΩ | 10 | 1
4.7kΩ | 10 | 1
15kΩ | 10 | 1
820Ω | 10 | 1
1kΩ | 10 | 1
20Ω | 10 | 1
10Ω | 10 | 1
Capacitors
4.7μF | 3 | 1.0908
0.1μF | 6 | 8.2548
100nF | 5 | 2.875
22μF | 3 | 1.4544
5.6nF | 1 | 0.52
4.7nF | 1 | 1.6622
1nF | 1 | 0.6
10nF | 1 | 0.8804
56pF | 1 | 0.8
100μF | 2 | 0.6666
Inductors
15μH | 1 | 1.13
10μH | 2 | 2.5
47μH | 1 | 1.13
LED
LED dome clear 5mm full colour rgb 4 pin | 2 | 23.2
LED 5mm clear Bi-colour red and green | 4 | 9.4
5 mm Red 2MCD | 2 | 2.4
5 mm Green 5MCD | 2 | 2.4
Blue 5mm 2200MCD | 1 | 3.94
Power LED white 10 W 12V | 1 | 30.7
Diodes
Zener diode | 10 | 3.8
Schottky | 2 | 5.8
Other components
Optocoupler | 6 | 28.5
Header SIL | 2 | 5
2N3904 | 2 | 8.76
Soldering wire 5 m | 1 | 8.78
Fuse glass 3 A | 10 | 20
Transord | 1 | 5.95
Terminal block PCB 2-way | 3 | 5.13
Terminal block PCB 3-way | 2 | 5.14
Fuse block cover | 4 | 23.24
Heatsink Mosfet | 1 | 8.8823
N-Mos | 1 | 8.4583
OP-Amp | 1 | 5.25
Socket 40 way SIL | 1 | 6
Header SIL 90 degree | 1 | 3.54
USB connector A type | 3 | 9.6
Breadboard Jumper wires kit | 1 | 96.49
Veroboard | 5 | 180
Heatsink Adhesive | 1 | 25
Battery | 1 | 279.1
Heatsink LED | 1 | 27.6
Connectors Solar Panel | 1 | 32
P-Mosfet | 2 | 45.4201
Arduino Uno | 1 | 401.53
40 W Solar Panel | 1 | 470
Total |  | 1828.5749
Budget |  | 1500
Expense |  | 328.5749

## I-V & P-V characterization
| 1000W/m^2 |  |  | 800W/m^2 |  |  | 600W/m^2 |  |  | 400W/m^2 |  |  | 200W/m^2
| Voltage | Current | Power | Voltage | Current | Power | Voltage | Current | Power | Voltage | Current | Power | Voltage | Current | Power
SC | 0 | 3.06 | 0 | 0 | 2.595 | 0 | 0 | 2.13 | 0 | 0 | 1.665 | 0 | 0 | 1.2 | 0
Max | 18 | 2.2222 | 40 | 16 | 1.7572 | 28.1156 | 14 | 1.2922 | 18.0911 | 12 | 0.82722 | 9.9267 | 10 | 0.36222 | 3.6222
OC | 22.1 | 0 | 0 | 20.1 | 0 | 0 | 18.1 | 0 | 0 | 16.1 | 0 | 0 | 14.1 | 0 | 0
FF |  |  | 0.59149 |  |  | 0.53903 |  |  | 0.46925 |  |  | 0.37031 |  |  | 0.21408
The fill factor (FF) is a measure of how far the I-V characteristics of an actual PV cell differ from those of an ideal cell

## Measurements of I-V & P-V
| 1000W/m^2 |  |  | Measured*
| Voltage | Current | Power | Voltage | Current | Power
SC | 0 | 3.06 | 0 | 0 | 2.8 | 0
Max | 18 | 2.2222 | 40 | 17.3 | 2.15 | 37.195
OC | 22.1 | 0 | 0 | 22 | 0 | 0
*Sun shine was not at optimal conditions